## Task Breakdown
Task Breakdown
Task Number | Task Description | Date Due (Planned) When you intend to complete the task | Date Completed (Actual) When you actually completed the task
1 | Finalyze task breakdown | 2025-03-13 | 2025-03-14
2 | Create user stories list | 2025-03-14 | 2025-03-14
3 | Sketch lo-fi wireframes, decide on theme, and draft design guide | 2025-03-14 | 2025-03-15
4 | Create starter file for code and connect to new Git Repo | 2025-03-14 | 2025-03-12
5 | Finalyze navigation bar, how information will be split across each page, and design guide | 2025-03-14 | 2025-03-15
6 | Finish half of the hi-fi wireframes on Figma | 2025-03-15 | 2025-03-15
7 | Finish all of hi-fi wireframes | 2025-03-15 | 2025-03-17
8 | Finish one webpage | 2025-03-17 | 2025-03-18
9 | Finish development plans | 2025-03-18 | 2025-03-18
10 | Finish half of webpage coding | 2025-03-21 | _____
11 | Finish all of webpage coding (draft but don't finalyze DOM/interactive elements) | 2025-03-22 | _____
12 | Draft questions and plan for user testing | 2025-03-23 | _____
13 | Finish DOM/interactive elements | 2025-03-23 | _____
14 | Ensure that existing code matches assignment requirements and user stories; locate anything that needs to be updated | 2025-03-23 | _____
15 | Finalize questions and plan for user testing | 2025-03-23 | _____
16 | Complete user testing and documentation | 2025-03-23 | _____
17 | Update any webpages based on user feedback | 2025-03-24 | _____
18 |  |  | _____
19 |  |  | _____
20 |  |  | _____
21 |  |  | _____
22 |  |  | _____
23 |  |  | _____
24 |  |  | _____